## Sheet1
CavLab Project
ID | Task Description | Start Date | Planned End Date | Actual End Date | Work Days Planned | Work Days Elapsed | Work Days Remain
3 | Electrical & Software Design | 2017-10-11 | 2017-11-25 | before 2018 | Finished!
3.1 | Source electronic components | 2017-10-11 | 2017-10-20 | before 2018 | Finished!
3.2 | Design control system | 2017-10-16 | 2017-11-25 | before 2018 | Finished!
5 | Control Implementation | 2018-01-15 | 2018-02-12 |  | 21 | 0 | 21
5.1 | Install ROS(platform) | 2018-01-15 | 2018-01-22 |  | Finished!
5.2 | Implement GPS related ros modules(navagation) | 2018-01-20 | 2018-02-12 |  | 16 | 0 | 16
5.3 | Implement speed and steer API(motion) | 2018-01-20 | 2018-02-12 |  | 16 | 0 | 16
5.4 | Implement udp communication modules(network) | 2018-02-01 | 2018-02-12 |  | 12 | 0 | 12
6 | Testing | 2018-02-12 | 2018-03-24 |  | 30 | 0 | 30
6.1 | Whole System Test | 2018-02-12 | 2018-02-19 |  | 6 | 0 | 6
6.2 | Bug fixes/improvements | 2018-02-19 | 2018-03-12 |  | 16 | 0 | 16
6.3 | Add cosmetic improvements | 2018-03-12 | 2018-03-19 |  | 6 | 0 | 6
6.4 | Final testing | 2018-03-19 | 2018-03-24 |  | 5 | 0 | 5
Formulas:
Planned End Date = MAX([Planned End Date, row below]:D5)
Work Days Planned = IF(ISBLANK([ID]),"",IF(OR(ISBLANK([Start Date]),ISBLANK([Planned End Date])),0,NETWORKDAYS([Start Date],[Planned End Date])))
Work Days Elapsed = IF(ISBLANK([ID]),"",IF(OR(ISBLANK([Start Date]),ISBLANK([Planned End Date])),0,IF(Today<[Start Date],0,NETWORKDAYS([Start Date],IF(ISBLANK([Actual End Date]),Today-1,[Actual End Date])))))
Work Days Remain = IF(ISBLANK([ID]),"",IF(OR(ISBLANK([Start Date]),ISBLANK([Planned End Date])),0,IF(OR(Today>[Planned End Date],NOT(ISBLANK([Actual End Date]))),0,IF(Today<[Start Date],NETWORKDAYS([Start Date],[Planned End Date]),NETWORKDAYS(Today,[Planned End Date])))))